## Requirements Stack
Requirement ID | Description | Story Points | Priority | Sprint No
1 | Setup basic web dotnet project scaffold | 2 | 1 | 1
2 | Build a basic WebSocket endpoint to for clients to connect to | 3 | 2 | 1
3 | Implement RoomHandler using the singleton design pattern to be able to create find and delete rooms | 5 | 3 | 1
4 | Implement frontends connection/state updates to backend (Join, Leave, click, sync, error) | 5 | 3 | 1
5 | Implement GameHandler for the board: Apply move, validate turn/update turn, detect win/draw, Allow for restarting | 8 | 3 | 1
6 | Frontend UI to show board | 5 | 2 | 1
7 | Allow for multiple rooms by way of urls | 5 | 4 | 2
8 | Allow for spectators of a game (So if player A-B is in a room if a third join it doesn't expect 3 players but puts 3rd as spectator) | 2 | 4 | 2
9 | In room chat (Can be based on a couple of preset messages. Think clash royale/chess.com where you have a "good game" button or something) | 3 | 6 | 3
10 | Setting up for basic win tracking/leaderboard display. Could be done with a full-stack salt + hash account creation or could be a simple "Enter your name" for simplicity | 5 | 5 | 2
11 | Unit testing applied to backend GameHandler/RoomHandler | 3 | 6 | 3
12 | Make site responsive/work properly on mobile/Different resolutions. (Done with breakpoints on frontend) | 5 | 7 | 3
13 | Data validation of types on backend to ensure low crash rate (Making sure "event" that was passed is a string "row" was a int, etc) | 3 | 5 | 2
14 | "Quick Play" i.e: button on homepage that allows one to search roomhandler for any 1 player room and join it. | 3 | 8 | 3
15 | Locking of room so you can't join through quick play but only link | 3 | 8 | 3
16 | Documentation | 5 | 9 | 3

## Sprint Planning Sheet
Description | Story Points | Priority | Status | Status Legend:
Sprint 1 |  |  |  | Done
Create static file server on the c# side. Test by navigating to the localhost url and receiving a file | 1 | High | Done | In Progress
front end methods for drawing to the canvas. Test by calling the methods either in the console/on main and validating it works for a number of states | 2 | High | Done | Not Started
Front/back end. Ensure that web sockets are connecting properly and data can be sent over. Test by printing data sent from both server and client | 2 | High | Not Started
Create the backend tic tac toe game handler. Test each function individually using print statements etc | 3 | High | Not Started
Create the roomhandler to handle message passing between players, this function should also own the websocket connection to the front end | 2 | High | Not Started
Handle user clicks on the front end. Test by ensuring an X or an O appears on the correct cell when clicked | 2 | High | In Progress
Roundup: finish any connection issues that may exists between other segments and ensure that tic tac toe is fully playable | 3 | High | Not Started
Checkpoint: Tic-Tac-Toe works as expected between two local players
Sprint Two
Edit the frontend/backend so that multiple rooms can be accessed through the URL. Test by having two different board states (in two tabs) at once | 3 | Medium | Not Started
Add game spectating. Test by having a third connection to a room that receives updates but can't make moves | 3 | Low | Not Started
Create a style guideline for what pages should generally look like: light/dark etc, also decide if we should use any additional css dependencies or others | 2 | Low | Not Started
Add extra styling to the tic tac toe webpage based on the style guidelines. test by navigating to the page | 2 | Low | Not Started
Create and style a landing page based on the style guidelines | 2 | Low | Not Started
Checkpoint: There is a landing page and both existing pages are styled. TTT can handle N simulatneous games without issues